## Internship Curriculum
Internship Curriculum & Timeline
Objective | Structural Finite Element Analysis of a Bucket Wheel Stacker cum Reclaimer
Project | BWSCR — Adani Krishnapatnam
Intern | Nikhil Mohan · Design Engineer Apprentice Trainee · EPC MHE Department
Mentor | Akshay Wadkar
Week | Phase | Task / Focus Area | Key Deliverable | Status
Phase 1 — Familiarisation & Analysis Preparation
Week 1 | Familiarisation | • In depth machine study — SCR operation from the material given • Review of GA drawings and CAD assembly. • Structural analysis theory and FEM Section II (loads and load combinations). | Study notes; familiarisation with model and standards | Done
Week 2 | Data Preparation | • Preparation of non-structural equipment load data — weights and mounting locations from BOM and CAD. • Commencement of mid surface geometry creation (Boom Structure). | Equipment load data sheet; Boom structure midsurfacing | Done
Week 3 | Geometry Preparation | • Completion of boom mid surface model (rear, mid, front sections). • Colour coding of surfaces by plate thickness commenced. | Boom mid surface model; colour coding begun | Done
Phase 2 — Mid Surface Modelling & Assembly
Week 4 | Geometry Preparation | • Assembly of boom sections into a single structure | Assembled, colour-coded boom structure | Done
Week 5 | Geometry Preparation | • Mid surface completion of mast / pylon & counterweight boom, along with color coding | Mast/pylon mid surface model completed | Done
Week 6 | Geometry Preparation | • Counterweight boom finishing; assembly of full SCR upper structure; quality check of the complete mid surface model. | Complete, quality-checked SCR mid surface model | Done
Phase 3 — Analysis Setup
Week 7 | FEMAP Setup | • Correction of midsurface model post reviewing • Import into FEMAP (Parasolid) • Material property research and definition (E350, Ck45, 42CrMo4) | Model imported and set up in FEMAP with materials defined | Done
Week 8 | Meshing & Properties | • Assignment of shell thickness properties by colour code • Meshing of the structure with shell elements • Mesh quality checks; merging of coincident nodes at interfaces. | Meshed FE model with properties assigned | Planned
Phase 4 — Loads, Boundary Conditions & Analysis
Week 9 | Load application | • Definition of boundary conditions. • Application of loads — self-weight, equipment, wind, and inertia. • As per FEM ISO standards: FEM Section II, ISO 5049, IS 800, IS 875 (Part 3). | Loads and boundary conditions applied | Planned
Week 10 | Analysis | • Definition of load case matrix and combinations per FEM Section II • linear static analysis (SOL 101) • verification against manual calculations | Solved analysis with verified load cases | Planned
Phase 5 — Results & Documentation
Week 11 | Post-Processing | • Result • Detection of max stress deflection points, nessecary action to be taken & re - anylsis within permissible limits | Verified Result against manual calculations & iterations defined for re-analysis | Planned
Week 12 | Reporting | • Compilation of the final analysis report — methodology, load cases, results, and conclusions. Final presentation to the team. | Final FEA report and presentation | Planned