## Internship Curriculum
Internship Curriculum & Timeline
Structural FEA of Bucket Wheel Stacker cum Reclaimer (SCR) ¦ Nikhil Mohan, Design Engineer Apprentice Trainee EPC MHE Dept., ISGEC Heavy Engineering Ltd., Pune ¦ Mentor: Akshay Wadkar
Week | Phase | Task / Focus Area | Key Deliverable | Status
Phase 1 — Familiarisation & Analysis Preparation
Week 1 | Familiarisation | Machine study — SCR operation, component breakdown, load paths; review of GA drawings and CAD assembly. Structural analysis theory and FEM Section II (loads and load combinations). Introductory FEMAP/Nastran exercise. | Study notes; familiarisation with model and standards | Done
Week 2 | Data Preparation | Preparation of non-structural equipment load data — weights and mounting locations from BOM and CAD. Commencement of mid surface geometry creation (boom). | Equipment load data sheet; boom mid surfacing begun | Done
Week 3 | Geometry Preparation | Completion of boom mid surface model (rear, mid, front sections). Colour coding of surfaces by plate thickness commenced. | Boom mid surface model; colour coding begun | Done
Phase 2 — Mid Surface Modelling & Assembly
Week 4 | Geometry Preparation | Assembly of boom sections into a single structure; corrections at section interfaces; colour coding of boom completed. | Assembled, colour-coded boom structure | Done
Week 5 | Geometry Preparation | Mid surface completion of mast / pylon assembly; colour coding of mast and counterweight boom commenced. | Mast/pylon mid surface model | Done
Week 6 | Geometry Preparation | Counterweight boom finishing; assembly of full SCR upper structure; quality check of the complete mid surface model. | Complete, quality-checked SCR mid surface model | Done
Phase 3 — Analysis Setup
Week 7 | FEMAP Setup | Correction of model per mentor review; import into FEMAP (Parasolid); material property research and definition (E350, Ck45, 42CrMo4); model orientation and coordinate system setup. | Model imported and set up in FEMAP with materials defined | Done
Week 8 | Meshing & Properties | Assignment of shell thickness properties by colour code; meshing of the structure with shell elements; mesh quality checks; merging of coincident nodes at interfaces. | Meshed FE model with properties assigned | Planned
Phase 4 — Loads, Boundary Conditions & Analysis
Week 9 | Model Setup | Definition of boundary conditions (slewing ring restraint) and connections (tension tie, pivots). Application of loads — self-weight, equipment, wind, and inertia. | Loads and boundary conditions applied | Planned
Week 10 | Analysis | Definition of load case matrix and combinations per FEM Section II; linear static analysis (SOL 101); verification of load–reaction equilibrium. | Solved analysis with verified load cases | Planned
Phase 5 — Results & Documentation
Week 11 | Post-Processing |  |  | Planned
Week 12 | Reporting | Compilation of the final analysis report — methodology, load cases, results, and conclusions. Final presentation to the team. | Final FEA report and presentation | Planned